## Self-Assessment (hidden)
Seft-Assessment
No | Criteria | MAX Score | 21127234 | 21127235 | 21127495 | 21127659
1 | Thực thi tất cả TCs và cập nhật Test Results Score = MIN(2, Number of updated TCs / 5) | 2 | 2 | 2 | 2 | 2
2 | Mỗi SV tìm và báo cáo ít nhất 5 bugs, thông tin bugs mô tả rõ ràng đầy đủ. Score = MIN(5, Number of Bugs) | 5 | 5 | 5 | 5 | 5
3 | Defect Serverity Distribution đầy đủ chính xác | 1 | 1 | 1 | 1 | 1
4 | Defect Summary đầy đủ, chính xác | 1 | 1 | 1 | 1 | 1
5 | Trình bày rõ ràng, đúng mẫu quy định | 1 | 1 | 1 | 1 | 1
| Total | 10 | 10 | 10 | 10 | 10

## Function List
ID | Function Name | Function detail | Remark
21127659 - Bùi Ngọc Kiều Nhi
Functional - GUI testing
1 | Functional testing for Create a new Requirement | Thêm Requirement mới
2 | Functional testing for Create a new Module | Thêm Module/Sub Module mới
3 | Functional testing for Create a new Report | Thêm Report mới
Performance testing
1 | Spike testing for Create a new Requirement
2 | Load testing for Create a new Requirement
3 | Stress testing for Create a new Requirement
Functional testing
1 | Functional for Create a new budget
2 | Functional for Create a new bill
API testing
1 | API for Create a new budget
2 | API for Create a new bill
3 | API for Create a new tag
GUI testing
1 | GUI for Create a new budget
2 | GUI for Create a new bill
3 | GUI for Create a new tag

## 21127234 - Anh Chi
No. | BugID | Status | Requirement Name | Summary | Steps to reproduce | Severity | Frequency | Priority | Attachment (Link to file) | Date | Reporter | Build
1 | 51860 | New | Search | [Search] When using any search bar that is available in the current release, submitting an SQL injection code leads to an error message of the third service saying the server is blocked. | Test environment: + OS: Window + Browser: Microsoft Edge Version 126.0.2592.56 (Official build) (64-bit) Steps: 1. Navigate to 'Project List' dashboard. 2. Enter as "' OR 1=1" in the search bar. 3. Press Enter or the magnifier icon. Expected result: The system notified user about the inappropriate input and asked user to do re-submit with other input. Actual result: The third service's error page appeared. | Major | Always | Normal | No | 2024-06-18 | 21127234 | Release 1
2 | 53698 | New | Register | [Functional - Register] User can use numeric values for FirstName field. | Test environment: + OS: Window + Browser: Microsoft Edge Version 126.0.2592.56 (Official build) (64-bit) Steps: 1. Access the website. 2. Press 'Sign Up' 3. Type in the First Name field: 123 4. Fill in other fields with valid value. 5. Press 'Save'. Expected result: The system notified user about the inappropriate input and asked user to do re-submit with other input. Actual result: The website accepts it as a valid value. | Minor | Always | Normal | No |  | 21127234 | Final
3 | 53703 | New | Register | [Functional - Register] System accepts string with only spaces in First Name field. | Test environment: + OS: Window + Browser: Microsoft Edge Version 126.0.2592.56 (Official build) (64-bit) Steps: 1. Access the website. 2. Press 'Sign Up' 3. Type in the First Name field: 4. Fill in other fields with valid value. 5. Press 'Save'. Expected result: The system notified user about the inappropriate input and asked user to do re-submit with other input. Actual result: The website accepts it as a valid value. | Major | Always | Normal | No |  |  | Final
4 | 52151 | Closed | CRUD-Administration | [Add - Administration] The system does not limit the number of characters in any data fields in user detail form. | - Environment: + OS: Window + Browser: Microsoft Edge Version 126.0.2592.56 (Official build) (64-bit) Steps: 1. Press the button "Add Users". 2. Enter in the First Name field: This is an example of a very long title that exceeds the character limit set for this field in order to test the validation and handling of such input by the system. 3. Fill in other fields with valid data. 4. Press the button "Save". Expected result: The website should display an error message indicating the invalid excessive input. Actual result: None of the error message was displayed. | Minor | Always | Normal | No |  |  | Release 2
5 | 52137 | Closed | CRUD-TestPlan | [Add - Test Plans] A new test plan is created even when the duration of the test was set unlogically. | - Environment: + OS: Window + Browser: Microsoft Edge Version 126.0.2592.56 (Official build) (64-bit) Steps: 1. Press the button 'Add Test Plans'. 2. Fill in these fields: Name, Description. 3. Fill in the Expiration & Assignment Time where the date in To is smaller than From: - From: 04/07/2024 - To: 28/06/2024 4. Press the button 'Save'. Expected result: The website should display an error message indicating the invalid input. Actual result: None of the error message was displayed. | Major | Always | Normal | No | 2024-09-07 | 21127234 | Release 2
6 | 52144 | Resolved | CRUD-TestPlan | [Edit - Test Plans] User can edit the test plan leaving the test name blanked. | - Environment: + OS: Window + Browser: Microsoft Edge Version 126.0.2592.56 (Official build) (64-bit) Steps: 1. Choose the test plan that needs editing 2. Press the pen icon at the end of the row containing that test plan. 3. Erase the value in the Name field. 4. Press "Save". Expected result: The website should display an error message indicating the invalid input. Actual result: The test plan was updated with an empty name. | Major | Always | High | No | 2024-09-07 | 21127234 | Release 2
7 | 52153 | Resolved | CRUD-Administration | [Add/Edit - Administration] Can create or update a user account with an email address that is already in use by another account. | - Environment: + OS: Window + Browser: Microsoft Edge Version 126.0.2592.56 (Official build) (64-bit) Steps: 1. Press the button "Add Users". 2. Fill in the Email field with an already existed email in the system: new123@gmail.com 3. Fill in other fields with valid values. 4. Press the button "Save". Expected result: The system should display an error message indicating that the email address is already in use, and the new account should not be created. Actual result: A new user was created with the already in use email. | Major | Always | High | No | 2024-09-07 | 21127234 | Release 2
8 | 53714 | New | Register | [Functional - Register] String contains special characters was accepted in FirstName field. | Test environment: + OS: Window + Browser: Microsoft Edge Version 126.0.2592.56 (Official build) (64-bit) Steps: 1. Access the website. 2. Press 'Sign Up' 3. Type in the First Name field: 123 4. Fill in other fields with valid value. 5. Press 'Save'. Expected result: The system notified user about the inappropriate input and asked user to do re-submit with other input. Actual result: The website accepts it as a valid value. | Minor | Always | Normal | No | 2024-08-27 | 21127234 | Final
9 | 53718 | New | Register | [Functional - Register] String contains special characters was accepted in LastName field. | Test environment: + OS: Window + Browser: Microsoft Edge Version 126.0.2592.56 (Official build) (64-bit) Steps: 1. Access the website. 2. Press 'Sign Up' 3. Type in the Last Name field: chr@as 4. Fill in other fields with valid value. 5. Press 'Save'. Expected result: The system notified user about the inappropriate input and asked user to do re-submit with other input. Actual result: The website accepts it as a valid value. | Minor | Always | Normal | No | 2024-08-27 | 21127234 | Final
10 | 53721 | New | CRUD-TestPlan | [Functional - Test Plan] Invalid year was accepted. | - Environment: + OS: Window + Browser: Microsoft Edge Version 126.0.2592.56 (Official build) (64-bit) Steps: 1. Press the button 'Add Test Plans'. 2. Fill in these fields: Name, Description. 3. Fill in the Date field: - From: 04/07/0202 - To: 28/06/2024 4. Press the button 'Save'. Expected result: The website should display an error message indicating the invalid input. Actual result: None of the error message was displayed. | Major | Always | Normal | No | 2024-08-27 | 21127234 | Final
<<< Insert New Line above this line >>>

## 21127235 - Quỳnh Chi
No. | BugID | Status | Requirement Name | Summary | Steps to reproduce | Severity | Frequency | Priority | Attachment (Link to file) | Date | Reporter | Build
1 | 53635 | New | CRUD-Issues | [Functionality - CRUD-Issues] The "Issue Title" field allows leading whitespace characters. | - Environment: Chrome - Phiên bản 127.0.6533.120 - Steps to reproduce: 1. Go to the Project List. 2. Select the Issue section. 3. Click on the "Add Issues" button. 4. Click on the Issue Title field. 5. Enter a single space into the Issue Title field. 6. Fill in the remaining fields. 7. Click on "Save" button. - Exptected behaviour: An error message appears in the Issue Title field. - Actual behaviour: The new issue has been successfully added.G2 | Major | Always | HIgh | https://cs.hcmus.edu.vn/mantisbt/view.php?id=53635 | 2024-08-26 | 21127235 | Final | 0
2 | 53640 | New | CRUD-Issues | [Functionality-CRUD-Issues] Incorrect category is allowed. | - Environment: Chrome - Phiên bản 127.0.6533.120 - Steps to reproduce: 1. Go to the Project List. 2. Select the Issue section. 3. Click on the "Add Issues" button. 4. Click on an existing issue in the list. 5. Click on Category fied. 6. Change the data in the Category field to "NotABugBug". 7. Click on "Save" button. - Exptected behaviour: An error message appears in the Category field. - Actual behaviour: The issue has been successfully updated. | Major | Always | HIgh | https://cs.hcmus.edu.vn/mantisbt/view.php?id=53640 | 2024-08-26 | 21127235 | Final
3 | 53655 | New | CRUD-Issues | [Functionality-CRUD-Issues] Incorrect issue type is allowed. | - Steps to reproduce: 1. Go to the Project List. 2. Select the Issue section. 3. Click on the "Add Issues" button. 4. Click on an existing issue in the list. 5. Click on Issue type fied. 6. Change the data in the Category field to "NotTrackingTracking". 7. Click on "Save" button. - Exptected behaviour: An error message appears in the Issue type field. - Actual behaviour: The issue has been successfully updated. | Major | Always | HIgh | https://cs.hcmus.edu.vn/mantisbt/view.php?id=53655 | 2024-08-26 | 21127235 | Final
4 | 53658 | New | CRUD-Issues | [Functionality-CRUD-Issues] Incorrect severity is allowed. | Environment: Chrome - Phiên bản 127.0.6533.120 Steps to reproduce: 1. Go to the Project List. 2. Select the Issue section. 3. Click on the "Add Issues" button. 4. Click on an existing issue in the list. 5. Click on severity fied. 6. Change the data in the severity field to "NotMajorMajor". 7. Click on "Save" button. Exptected behaviour: An error message appears in the severity field. Actual behaviour: The issue has been successfully updated. | Major | Always | HIgh | https://cs.hcmus.edu.vn/mantisbt/view.php?id=53658 | 2024-08-26 | 21127235 | Final
5 | 53661 | New | CRUD-Issues | [Functionality-CRUD-Issues] Incorrect status is allowed. | Environment: Chrome - Phiên bản 127.0.6533.120 Steps to reproduce: 1. Go to the Project List. 2. Select the Issue section. 3. Click on the "Add Issues" button. 4. Click on an existing issue in the list. 5. Click on status fied. 6. Change the data in the status field to "NotMajorMajor". 7. Click on "Save" button. Exptected behaviour: An error message appears in the status field. Actual behaviour: The issue has been successfully updated. | Major | Always | HIgh | https://cs.hcmus.edu.vn/mantisbt/view.php?id=53661 | 2024-08-26 | 21127235 | Final
6 | 53667 | New | CRUD-Issues | [Functionality-CRUD-Issues] The status field must be a required field. | Environment: Chrome - Phiên bản 127.0.6533.120 Steps to reproduce: 1. Go to the Project List. 2. Select the Issue section. 3. Click on the "Add Issues" button. 4. Fill in all the fields but leave blank at the status field. 5. Click on "Save" button. Exptected behaviour: An error message appears in the status field. Actual behaviour: The new issue has been successfully added. | Major | Always | HIgh | https://cs.hcmus.edu.vn/mantisbt/view.php?id=53667 | 2024-08-26 | 21127235 | Final
7 | 53673 | New | CRUD-Issues | [Functionality-CRUD-Issues] Allow entering a non-existent test run. | Environment: Chrome - Phiên bản 127.0.6533.120 Steps to reproduce: 1. Go to the Project List. 2. Select the Issue section. 3. Click on the "Add Issues" button. 4. Fill in all the fields. 5. Fill in a non-existent test run: "Nothing" 5. Click on "Save" button. Exptected behaviour: An error message appears in the test run field. Actual behaviour: The new issue has been successfully added. | Major | Always | HIgh | https://cs.hcmus.edu.vn/mantisbt/view.php?id=53673 | 2024-08-26 | 21127235 | Final
8 | 53677 | New | CRUD-Issues | [Functionality-CRUD-Issues] Incorrect priority is allowed. | Environment: Chrome - Phiên bản 127.0.6533.120 Steps to reproduce: 1. Go to the Project List. 2. Select the Issue section. 3. Click on the "Add Issues" button. 4. Click on an existing issue in the list. 5. Click on priority fied. 6. Change the data in the priority field to "NotHighHigh". 7. Click on "Save" button. Exptected behaviour: An error message appears in the priority field. Actual behaviour: The issue has been successfully updated. | Major | Always | HIgh | https://cs.hcmus.edu.vn/mantisbt/view.php?id=53677 | 2024-08-26 | 21127235 | Final
9 | 53680 | New | CRUD-Releases | [Functionality-CRUD-Releases] The "Release Title" field allows leading whitespace characters. | Environment: Chrome - Phiên bản 127.0.6533.120 Steps to reproduce: 1. Go to the Project List. 2. Select the Releases section. 3. Click on the "Add Releases" button. 4. Enter a single space into the release name field. 5. Fill in remaining field. 6. Click on "Save" button. Exptected behaviour: An error message appears in the release name field. Actual behaviour: The release has been successfully added. | Major | Always | HIgh | https://cs.hcmus.edu.vn/mantisbt/view.php?id=53680 | 2024-08-26 | 21127235 | Final
10 | 53684 | New | CRUD-Issues | [Functionality-CRUD-Releases] The data in the Type field duplicates the data in the Description field. | Environment: Chrome - Phiên bản 127.0.6533.120 Steps to reproduce: 1. Go to the Project List. 2. Select the Releases section. 3. Click on the "Add Releases" button. 4. Fill in all fields. 6. Click on "Save" button. Exptected behaviour: The data in the Type field duplicates the data in the Description field. Actual behaviour: The data in the Type field and the data in the Description field is different. | Major | Always | HIgh | https://cs.hcmus.edu.vn/mantisbt/view.php?id=53684 | 2024-08-26 | 21127235 | Final
<<< Insert New Line above this line >>> |  |  |  |  | 1. Go to the Project List.
2. Select the Releases section.
3. Click on the "Add Releases" button.
4. Enter a single space into the release name field.
5. Fill in remaining field.
6. Click on "Save" button.
Exptected behaviour: An error message appears in the release name field.
Actual behaviour: The release has been successfully added.

## 21127495 - Cát
No. | BugID | Status | Requirement Name | Summary | Steps to reproduce | Severity | Frequency | Priority | Attachment (Link to file) | Date | Reporter | Build
1 | CRUD-Test Run-TC002 | GUI&Usability | CRUD-Test Run | Verify that Test run list page is responsive and displays correctly on different screen sizes | 1. Navigate to the "Test run list" page. 2. Resize the browser window to different screen sizes. 3. Observe the elements displayed. | Minor | Always | Normal | 52236 | 2024-07-08 | 21127495 | Release 2
2 | CRUD-Test Run-TC009 | Functional | CRUD-Test Run | Ensure that a new test run is created when filling the field "Assign to" with "Unknown" like the test runs created previously. | 1. Navigate to the "Test run list" page. 2. Click "Add Test Runs" button. 3.Fill in textbox "Name" with "Vic test 1 . 4. Fill in field "Assigned to" with "Unknown". 5. Select "Test update 1" in field "Test Case". 6. Click "Save" button. | Major | Always | High | 52243 | 2024-07-08 | 21127495 | Release 2
3 | CRUD-Test Run-TC010 | Functional | CRUD-Test Run | Ensure that a new test run cannot be created when filling the field "Assign to" with the inactive user. | 1. Navigate to the "Test run list" page. 2. Click "Add Test Runs" button. 3.Fill in textbox "Name" with "Vic test 1 . 4. Fill in field "Assigned to" with "trung nguyen". 5. Select "Test update 1" in field "Test Case". 6. Click "Save" button. | Major | Always | High | 52246 | 2024-07-08 | 21127495 | Release 2
4 | CRUD-Test Run-TC003 | GUI&Usability | CRUD-Test Run | Verify that Test run with 290-character name can be displayed correctly in the tittle column after being created | 1. Navigate to the "Test run list" page. 2. Click "Add Test Runs" button. 3. Fill in textbox "Name" with "Vic test 12346789101112131415161718192021222324252627282930313233343536373839404142434445464748495051525354555657585960616263646566676869707172737475767778798081828384858687888990919293949596979899100101102103104105106107108109110111112113114115116117118119120121122123124125126127128129130" . 4. Fill "nguyen an" in field "Assigned to". 5. Select "Test update 1" in field "Test Case". 6. Click "Save" button. | Major | Always | High | 52241 | 2024-07-08 | 21127495 | Release 2
5 | CRUD-Test Run-TC014 | Functional | CRUD-Test Run | Ensure that the test run name can be updated successfully. | 1. Navigate to the "Test run list" page. 2. Go to page 6 of the list. 3.Click the update icon (pencil icon) of the test run with title "Test run to test update function 1". 4. Details of the test run are displayed. 5. Fill "Rename test run" in field "Name" and keep the remaining fields unchanged. 6. Click "Save" button. | Major | Always | High | 52254 | 2024-07-08 | 21127495 | Release 2
6 | CRUD-Test Run-TC015 | Functional | CRUD-Test Run | Ensure that the test run version can be updated successfully. | 1. Navigate to the "Test run list" page. 2. Go to page 6 of the list. 3.Click the update icon (pencil icon) of the test run with title "Test run to test update function 1". 4. Details of the test run are displayed. 5. Fill "4" in field "Version" and keep the remaining fields unchanged. 6. Click "Save" button. | Major | Always | High | 52258 | 2024-07-08 | 21127495 | Release 2
7 | CRUD-Test Run-TC016 | Functional | CRUD-Test Run | Ensure that the test run browser can be updated successfully. | 1. Navigate to the "Test run list" page. 2. Go to page 6 of the list. 3.Click the update icon (pencil icon) of the test run with title "Test run to test update function 1". 4. Details of the test run are displayed. 5. Fill "Chrome" in field "Browser" and keep the remaining fields unchanged. 6. Click "Save" button. | Major | Always | High | 52259 | 2024-07-08 | 21127495 | Release 2
8 | CRUD-Test Run-TC017 | Functional | CRUD-Test Run | Ensure that the test run assignee can be updated successfully (updating with existed user). | 1. Navigate to the "Test run list" page. 2. Go to page 6 of the list. 3.Click the update icon (pencil icon) of the test run with title "Test run to test update function 1". 4. Details of the test run are displayed. 5. Fill "new name" in field "Assign to" and keep the remaining fields unchanged. 6. Click "Save" button. | Major | Always | High | 52260 | 2024-07-08 | 21127495 | Release 2
9 | CRUD-Test Run-TC018 | Functional | CRUD-Test Run | Ensure that the test case of a test run can be updated successfully. | 1. Navigate to the "Test run list" page. 2. Go to page 6 of the list. 3.Click the update icon (pencil icon) of the test run with title "Test run to test update function 1". 4. Details of the test run are displayed. 5. Fill "Test Import" in field "Test Case" and keep the remaining fields unchanged. 6. Click "Save" button. | Major | Always | High | 52261 | 2024-07-08 | 21127495 | Release 2
10 | CRUD-Test Run-TC019 | Functional | CRUD-Test Run | Ensure that the test run description can be updated successfully. | 1. Navigate to the "Test run list" page. 2. Go to page 6 of the list. 3.Click the update icon (pencil icon) of the test run with title "Test run to test update function 1". 4. Details of the test run are displayed. 5. Fill "This is test input" in field "Description" and keep the remaining fields unchanged. 6. Click "Save" button. | Major | Always | High | 52263 | 2024-07-08 | 21127495 | Release 2
11 | Update-User-TC03 | Functional | Update-User | Ensure that user information cannot be updated with valid first name (Only spaces string) | 1. Enter First Name: " " 2. Enter Last Name: "abc" 3. Enter Email: "lnscat21@fit.hcmus.edu.vn" 4. Enter Language: "English" 5. Choose Status: "Active" 6. Choose User Designation: "Developer" 7. Upload photo: "abc.png" 8. Choose Locale: "Vietnamese (Vietnam)" 9. Choose Timezone: "(UTC) London" 10. Click "Save" button | Major | Always | High |  | 2024-08-26 | 21127495 | Final
12 | Update-User-TC02 | Functional | Update-User | Ensure that user information cannot be updated with invalid first name (> 255 characters) | 1. Enter First Name: "1234567891011121314151617181920212223242526272829303132333435363738394041424344454647484950 1234567891011121314151617181920212223242526272829303132333435363738394041424344454647484950 123456789101112131415161718192021222324252627282930313233343536373839403s" 2. Enter Last Name: "abc" 3. Enter Email: "lnscat21@fit.hcmus.edu.vn" 4. Enter Language: "English" 5. Choose Status: "Active" 6. Choose User Designation: "Developer" 7. Upload photo: "abc.png" 8. Choose Locale: "Vietnamese (Vietnam)" 9. Choose Timezone: "(UTC) London" 10. Click "Save" button | Minor | Always | Normal |  | 2024-08-26 | 21127495 | Final
13 | Update-User-TC03 | Functional | Update-User | Ensure that user information cannot be updated with valid first name (Only spaces string) | 1. Enter First Name: " " 2. Enter Last Name: "abc" 3. Enter Email: "lnscat21@fit.hcmus.edu.vn" 4. Enter Language: "English" 5. Choose Status: "Active" 6. Choose User Designation: "Developer" 7. Upload photo: "abc.png" 8. Choose Locale: "Vietnamese (Vietnam)" 9. Choose Timezone: "(UTC) London" 10. Click "Save" button | Major | Always | High |  | 2024-08-26 | 21127495 | Final
14 | Update-User-TC02 | Functional | Update-User | Ensure that user information cannot be updated with invalid first name (> 255 characters) | 1. Enter First Name: "1234567891011121314151617181920212223242526272829303132333435363738394041424344454647484950 1234567891011121314151617181920212223242526272829303132333435363738394041424344454647484950 123456789101112131415161718192021222324252627282930313233343536373839403s" 2. Enter Last Name: "abc" 3. Enter Email: "lnscat21@fit.hcmus.edu.vn" 4. Enter Language: "English" 5. Choose Status: "Active" 6. Choose User Designation: "Developer" 7. Upload photo: "abc.png" 8. Choose Locale: "Vietnamese (Vietnam)" 9. Choose Timezone: "(UTC) London" 10. Click "Save" button | Minor | Always | Normal |  | 2024-08-26 | 21127495 | Final

## 21127659 - Nhi
No. | BugID | Status | Requirement Name | Summary | Steps to reproduce | Severity | Frequency | Priority | Attachment (Link to file) | Date | Reporter | Build
1 | 53583 | New | Add Requirement | [Add - Requirement] Users can successfully add a requirement with description fields containing special characters | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to Project List. 6. Select Project Alpha. 7. Select section "Requirements". 8. Click on "Add requirement" button. 9. Select "Version 2.0" in Release field. 10. Select "abc" in Requirement Type field. 11. Enter Requirement Description field: "any emoji". 12. Click on "Save" button. Expected behavior: 1. Do not allow users to enter special characters. 2. Re-enter required. Actual behavior: The newly added requirement is displayed on the interface. | Feature | Always | Low | https://drive.google.com/file/d/1DNuK66J0O7o3JrYt7ZgyfngILfwrDSfu/view?usp=sharing | 2024-08-26 | 21127659 | Final | 0
2 | 53584 | New | Add Requirement | [Add - Requirement] The system doesn't limit the maximum number of characters a user can enter for the Description field. | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to Project List. 6. Select Project Alpha. 7. Select section "Requirements". 8. Click on "Add requirement" button. 9. Select "Version 2.0" in Release field. 10. Enter "abc" in Requirement Type field. 11. Enter Requirement Description field: "1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 1234567890 ". 12. Click on "Save" button. Expected behavior: Users are only allowed to enter a maximum of 255 characters. Actual behavior: The newly added requirement is displayed on the interface. | Trivial | Always | Low | https://drive.google.com/file/d/15UBR_0x4wEYOtorbqDiyNbq1c6mBZFrg/view?usp=sharing | 2024-08-26 | 21127659 | Final
| 53585 | New | Add Requirement | [UIUX - Requirement] Text content is not properly aligned. | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to Project List. 6. Select Project Alpha. 7. Select section "Requirements". 8. Look at the "description" column. Expected behavior: Rows and columns should be aligned evenly Actual behavior: In the description column, the content is aligned inward compared to the title | Tweak | Always | Normal | https://drive.google.com/file/d/1T2WnSfBIr0JO-In1cjiUY1vD6WR0-5CP/view?usp=sharing | 2024-08-26 | 21127659 | Final
| 53586 | New | Add Requirement | [UIUX - Requirement] The Select Release field does not have a mandatory marking. | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to Project List. 6. Select Project Alpha. 7. Select section "Requirements". 8. Click on "Add requirement" button. 9. Observe the elements displayed. Expected behavior: Mandatory input fields should be marked Actual behavior: There is no mark in the required field Select Release | Tweak | Always | Normal | https://drive.google.com/file/d/1bnqXs2CBOZZ-91sDvBgPjpdI_teuAtsG/view?usp=sharing | 2024-08-26 | 21127659 | Final
| 53587 | New | Add Requirement | [UIUX - Requirement] Title is not centered relative to input field. | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to the "Project list" page. 6. Choose project name "Project Alpha". 7. Select "Reports" on the navbar. 8. Click "Add Report" button. Expected behavior: Title is centered relative to input field. Actual behavior: The title is offset above the input field. | Trivial | Always | Low | https://drive.google.com/file/d/1ZiwPG-qL2nxGjoa-3xrBqyr8UEeVlypU/view?usp=sharing | 2024-08-26 | 21127659 | Final
2 | 53588 | New | Add Report | [UIUX - Report] Duration is not mandartory marking if blank. | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to the "Project list" page. 6. Choose project name "Project Alpha". 7. Select "Reports" on the navbar. 8. Click "Add Report" button. 9. Press the button "Save and add". Expected behavior: The title and duration fields should be marked with an x Actual behavior: The duration field is checked even though no data has been entered. | Tweak | Always | Low | https://drive.google.com/file/d/142BNlNlpROXwI55Pk3mj0fpBiXV5HRJM/view?usp=sharing | 2024-08-26 | 21127659 | Final
| 53589 | New | Add Report | [Add - Report] The system automatically changes to 200y format when adding a report with a start date of 000y format. | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login 3. Enter username: "123@1234 4. Enter password: "123". 5. Navigate to the "Project list" page. 6. Choose project name "Project Alpha". 7. Select "Reports" on the navbar. 8. Press "Add report" button. 9. Fill in Duration from: "09/07/0004 12:00 SA". 10. Fill in Duration to: "08/07/2024 12:00 SA". 11. Fill in title fields: "abc". 12. Press "Save and add" button. Expected behavior: 1. The new report can not created, and a message is displayed. 2. Ask the user to re-enter. Actual behavior: The new report was created successfully but the system arbitrarily changed it to 200y format. | Major | Always | High | No | 2024-08-26 | 21127659 | Final
2 | 53590 | New | Add Report | [Add - Report] The system automatically changes to 20yy format when adding a report with a end date of 00yy format. | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login [^] 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to the "Project list" page. 6. Choose project name "Project Alpha". 7. Select "Reports" on the navbar. 8. Press "Add report" button. 9. Fill in Duration from: "09/07/0040 12:00 SA". 10. Fill in Duration to: "08/07/2024 12:00 SA". 11. Fill in title fields: "abc". 12. Press "Save and add" button. Expected behavior: 1. The new report can not created, and a message is displayed. 2. Ask the user to re-enter. Actual behavior: The new report was created successfully but the system arbitrarily changed it to 2040. | Major | Always | High | No | 2024-08-26 | 21127659 | Final
| 53591 | New | Add Report | [Add - Report] The system automatically changes to 2yyy format when adding a report with a start date of 0yyy format. | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to the "Project list" page. 6. Choose project name "Project Alpha". 7. Select "Reports" on the navbar. 8. Press "Add report" button. 9. Fill in Duration from: "09/07/0240 12:00 SA". 10. Fill in Duration to: "08/07/2024 12:00 SA". 11. Fill in title fields: "abc". 12. Press "Save and add" button. Expected behavior: 1. The new report can not created, and a message is displayed. 2. Ask the user to re-enter. Actual behavior: The new report was created successfully but the system arbitrarily changed it to 2240 format. | Major | Always | High | No | 2024-08-26 | 21127659 | Final
| 53592 | New | Add Report | [Add - Report] Redirect to error page when adding a report with start date in the form dd/mm/yyyyy --:-- | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to the "Project list" page. 6. Choose project name "Project Alpha". 7. Select "Reports" on the navbar. 8. Press "Add report" button. 9. Fill in Duration from: "09/07/20240 12:00 SA". 10. Fill in Duration to: "08/07/2024 12:00 SA". 11. Fill in title fields: "abc". 12. Press "Save and add" button. Expected behavior: 1. The new report can not created, and a message is displayed. 2. Ask the user to re-enter. Actual behavior: Navigate to error message page. | Major | Always | High | https://drive.google.com/file/d/1ksEml6r9pvFeB2LorRJ_xajqAwcbqbCB/view?usp=sharing | 2024-08-26 | 21127659 | Final
2 | 53593 | New | Add Report | [Add - Report] Redirect to error page when adding a report with end date in the form dd/mm/yyyyy --:-- | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login [^] [^] 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to the "Project list" page. 6. Choose project name "Project Alpha". 7. Select "Reports" on the navbar. 8. Press "Add report" button. 9. Fill in Duration from: "09/07/2024 12:00 SA". 10. Fill in Duration to: "08/07/20240 12:00 SA". 11. Fill in title fields: "abc". 12. Press "Save and add" button. Expected behavior: 1. The new report can not created, and a message is displayed. 2. Ask the user to re-enter. Actual behavior: Navigate to error message page. | Major | Always | High | https://drive.google.com/file/d/1ksEml6r9pvFeB2LorRJ_xajqAwcbqbCB/view?usp=sharing | 2024-08-26 | 21127659 | Final
| 53594 | New | Add Report | [UIUX - Report] System does not hghlight the keyword. | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to the "Project list" page. 6. Choose project name "Project Alpha". 7. Select "Reports" on the navbar. 8. Fill in search fields: "Test". 9. Press Enter. Expected behavior: 1. Returns search results with the keyword highlighted. 2. Or let user know the keyword they are finding by leaving keyword in search bar. Actual behavior: Keywords are not highlighted or displayed in the search bar. | Tweak | Always | Normal | No | 2024-08-26 | 21127659 | Final
2 | 53595 | New | Add Report | [UIUX - Report] System do not automatically navigate to the found page 1 | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to the "Project list" page. 6. Choose project name "Project Alpha". 7. Select "Reports" on the navbar. 8. Select page 5. 9. Fill in search fields: "aa". 10. Press Enter. Expected behavior: Returns search results with the keyword highlighted at page 1. Actual behavior: Returns search results with the keyword highlighted at page 5. | Minor | Always | Normal | https://drive.google.com/file/d/17pZd-4SogrjR8RK2zVJXhxQcuzIhiFnY/view?usp=sharing | 2024-08-26 | 21127659 | Final
| 53596 | New | Add Report | [UIUX - Report] Text content in table is not properly aligned. | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login [^] 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to Project List. 6. Select Project Alpha. 7. Select section "Reports". 8. Look at each row in table. Expected behavior: All rows should be aligned evenly Actual behavior: The rows in the table are not aligned. | Tweak | Always | Low | https://drive.google.com/file/d/1BBHWAJafFMxgor-lhf7LBauaQtCcqtZ0/view?usp=sharing | 2024-08-26 | 21127659 | Final
| 53597 | New | Add Module | [UIUX - Module] Modules are not highlighted when user clicks view | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login [^] 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to the Project List page. 6. Choose project name "Project Alpha". 7. Select "Modules" on the navbar. 8. Select "Dashboard". Expected behavior: 1. Display Dashboard sub modules. 2. Modules Dashboard is highlighted. Actual behavior: 1. Display Dashboard sub modules. 2. Modules Dashboard is not highlighted. | Tweak | Always | Normal | No | 2024-08-26 | 21127659 | Final
| 53598 | New | Add Module | [Add - Module] Sub-modules are hidden after adding a new module. | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to the Project List page. 6. Choose project name "Project Alpha". 7. Select "Modules" on the navbar. 8. Select "Dashboard". 9. Select "Add Module" icon in "Dashboard" box. 10. Enter the module name: "Test module". 11. Select "Yes" button to confirm. Expected behavior: 1. Notification of successful module addition. 2. Submodules are still visible for easy tracking. Actual behavior: 1. Add modules successfully. 2. Reload the page and hide the submodules I opened before. | Trivial | Always | Low | No | 2024-08-26 | 21127659 | Final
| 53599 | New | Add Module | [UIUX - Module] There is no way to disable opened modules. | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to the Project List page. 6. Choose project name "Project Alpha". 7. Select "Modules" on the navbar. 8. Select "Dashboard". 9. Select "User Management". 10. Select "Ship and Delivery". 11. Select "Test module". 12. Observe the results received. Expected behavior: There is an icon on each module to hide after opening Actual behavior: There is no icon on each module to hide after opening | Minor | Always | Normal | No | 2024-08-26 | 21127659 | Final
2 | 53600 | New | Add Module | [Add - Module] User can add a new module leaving the module name containing only spaces | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to the Project List page. 6. Choose project name "Project Alpha". 7.. Select "Modules" on the navbar. 8. Press "Add Modules" button. 9. Leave the module name blanked: " ". 10. Press the button "Save". Expected behavior: The website should display an error message indicating the invalid input. Actual behavior: The new test plan is created successfully, and page is reloaded. | Major | Always | High | https://drive.google.com/file/d/1-8zA7e5CyYjmbm4y7Y1zWx1GjlqctZBu/view?usp=sharing | 2024-08-26 | 21127659 | Final
| 53601 | New | Add Module | [UIUX - Module] user can add a new module with Module Name field containing special characters. | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Open browser. 2. Navigate to: https://localhost:4000/login 3. Enter username: "123@1234". 4. Enter password: "123". 5. Navigate to the Project List page. 6. Choose project name "Project Alpha". 7. Select "Modules" on the navbar. 8. Press "Add Modules" button. 9. Enter the module name: "any emoji". 10. Press the button "Save". Expected behavior: The website should display an error message indicating the invalid input. Actual behavior: The new test plan is created successfully, and page is reloaded. | Feature | Always | Low | No | 2024-08-26 | 21127659 | Final
| 52126 | Closed | Add Report | [UIUX - Report] The Report page reload when collapsing the sidebar. | Environment: + OS: Window + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Navigate to the "Project list" page. 2. Choose project name "Project Alpha". 3. Select "Reports" on the navbar. 4. Scroll down to the bottom of the page. 5. Select the toggle sidebar button on the right to collapse the sidebar. Expected result: The sidebar should be collapse without reload page. Actual result: The sidebar will collapse but the page reloads or still remains at the bottom of the page. | Tweak | Always | Normal | No | 2024-07-09 | 21127659 | Release 2
| 52128 | Closed | Add Report | [UIUX - Report] The collapsing sidebar expands when moving to the next page of report list. | Environment: + OS: Window + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Navigate to the "Project list" page. 2. Choose project name "Project Alpha". 3. Select "Reports" on the navbar. 4. Select the toggle sidebar button on the right to collapse the sidebar. 5. Navigate to second page of the report list. Expected result: The sidebar will still be collapsed after navigating to another page. Actual result: The redirect was successful but the sidebar is hidden. | Minor | Always | Normal | No | 2024-07-09 | 21127659 | Release 2
| 52156 | Closed | Add Report | [Add - Report] Navigate to error notice page when creating a report with the input date is not valid. | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Navigate to the "Project list" page. 2. Choose project name "Project Alpha". 3. Select "Reports" on the navbar. 4. Press "Add report" button. 5. Fill in Duration from: "09/07/2024". 6. Fill in Duration to: "08/07/2024". 7. Fill in title fields: "abc". 8. Press Enter. Expected behavior: 1. The new report can not created, and a message is displayed. 2. Ask the user to re-enter. Actual behavior: Navigate to error notice page. | Major | Always | High | No | 2024-07-09 | 21127659 | Release 2
| 52132 | Closed | Add Report | [UIUX - Report] Showing all page numbers of total reports after returning report search results. | Environment: + OS: Windows 11 + Browser: Cốc cốc version 130.0.172 (Offical build) (32 bit) Steps: 1. Navigate to the "Project list" page. 2. Choose project name "Project Alpha". 3. Select "Reports" on the navbar. 4. Press "Add report" button. 5. Fill in search fields: "Test". 6. Press Enter. Expected behavior: 1. Returns search results. 2. Only page 1 is displayed in the page number section, because the search results only have 3 reports. Actual behavior: 1. Returns search results. 2. Displays all page numbers of the total report. | Major | Always | High | No | 2024-07-09 | 21127659 | Release 2
<<< Insert New Line above this line >>>

## Requirement List (hidden)
No. | ID | Requirement Name | Details | Remark
1 | R001 | Home | Hiển thị thông tin tất cả các Article (trang chủ - Home). Thông tin một article bao gồm hình đại diện, tiêu đề và mô tả tóm tắt, 1 dòng hiển thị tối đa 3 articles.
2 | R002 | Register | Đăng ký tài khoản người dùng mới
3 | R003 | Login | Đăng nhập vào hệ thống
4 | R004 | Details | Hiển thị thông tin chi tiết về Article bao gồm: Hình đại diện, mô tả chi tiết, danh sách comment.
5 | R005 | Comments - Pagination | Mỗi trang hiển thị tối đa 3 comment. Thông tin của một comment bao gồm nội dung comment và thời gian đăng.
6 | R006 | Add Comment | Chỉ có tài khoản đã đăng nhập mới được thêm Comment
7 | R007 | Delete Comment | Chỉ có Admin mới được xóa Comment
<<< Insert New Line above this line >>>

## Defect Severity Distribution
DEFECT SEVERITY DISTRIBUTION
No. | Requirement Name | Block | Crash | Major | Minor | Tweak | Text | Trivial | Feature | Total | Fixed | Not fixed
1 | Add Requirement | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 1 | 5 | 0 | 5
2 | Add Module | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 5 | 0 | 5
3 | Add Report | 0 | 0 | 7 | 2 | 4 | 0 | 0 | 0 | 13 | 4 | 9
<<< Insert New Line above this line >>> | Total | 0 | 0 | 8 | 3 | 7 | 0 | 3 | 2 | 23 | 4 | 19

## Summary
Bug found per tester with priority
Tester Name | Immediate | Urgent | High | Normal | Low | Subtotal
21127234 | 0 | 0 | 2 | 6 | 0 | 8
21127235 | 0 | 0 | 10 | 0 | 0 | 10
21127495 | 0 | 0 | 11 | 3 | 0 | 14
21127659 | 0 | 0 | 8 | 8 | 7 | 23
Total | 55
Bug found per tester today and total so far
Tester Name | # Bugs Found Today | # Bug found so far
21127234 | 3 | 8
21127235 | 0 | 10
21127495 | 0 | 14
21127659 | 0 | 23
Total | 3 | 55
Bug found per build
Build | # of Bug Found | # of Bug Closed | # Bug Reopened | Date
Release 01 | 0 | 0 | 0 | 2024-08-27
Release 02 | 0 | 0 | 0 | 2024-08-27
Final | 38 | 0 | 0 | 2024-08-27
Total | 38 | 0 | 0
Formulas:
Immediate = COUNTIFS('21127234 - Anh Chi'!$L:$L,[Tester Name],'21127234 - Anh Chi'!$K:$K,TODAY())
Immediate = COUNTIFS('21127235 - Quỳnh Chi'!$L:$L,[Tester Name],'21127235 - Quỳnh Chi'!$K:$K,TODAY())

## Legend
Priority
Immediate
Urgent
High
Normal
Low
Defect Status
New
Closed
Reopened
Severity | Description
Block | critical negative impact; this issue is holding up progress on another issue/task/project
Crash | severe negative impact; hardware/software necessary for job duties is crashed/crashing
Major | large negative impact; no workaround available
Minor | medium negative impact; no workaround available
Tweak | small negative impact; workaround is unavailable or is very complex/inefficient
Text | tiny negative impact; text-based content needs updated
Trivial | annoyance/hindrance; a simple workaround is available
Feature | no negative impact on current processes; request for additional functionality
Frequency
Always
Sometimes
Random
Have not tried
Unable to reproduce
None